## Sheet1
Test Report
Project Name | Sauce Demo Website
Test Date | From 26 April 2025 to 5 May 2025
Environment | OS 11'10 Intel Core i5 / i7 ●RAM: Min 8GB (Rec: 16GB) ●Storage: At least 50GB free space
Test Cycle | PASSED | FAILED | EXECUTED | PENDING | BLOCKD | TOTAL
Manual Tests | 35 | 1 | 36 | 0 | 0 | 36
Automation Tests | 22 | 0 | 14 | 0 | 0 | 22
Feature/compoents | Type | Tests Planned | % Test Executed | % Test Passed | % Deferred/ blocked | Status | Observations
Product page | Manual | 14 | 100% | 100% | 0 | Completed | Successfully implemented
Product page | Automation | 15 | 100% | 100% | 0 | Completed | Successfully implemented
Cart page | Manual | 14 | 100% | 93% | 0 | Completed | problem in cart
Cart page | Automation | 7 | 100% | 100% | 0 | Completed | Successfully implemented
Checkout | Manual | 8 | 100% | 100% | 0 | Completed | Successfully implemented